## Report
From |  | 2026-09-01 |  | To | 2026-09-30
Projects |  | Institute of Internal Auditors
Filters |  | Users: Mustafizur Rahman, Foysal Rabbi
Time Zone |  | America/New_York
Generated on |  | 2026-10-07T06:09:19-04:00
Report Time Format |  | Hours
Worklog Author | Total Worklog Author | Issue (Key Summary) | Total Issue (Key Summary) | Client Reference
Foysal Rabbi | 42.5 | IOIA-5220 Unexpected Failure During HubSpot Certification Synchronization | 1
|  | IOIA-5234 Webinar Teaser Card Dates | 1 | TPX-1162
|  | IOIA-5248 Stripe charge discrepancy when quote is converted with different tax-rate address | 4 | TPX-1378
|  | IOIA-5262 Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 11.5
|  | IOIA-5323 Test (UAT & Prod): Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | 1.5 | TPX-1088
|  | IOIA-5327 Test (UAT & Prod): Update AI Certs Enrollment Validation and Handoff for Course 1 and Course 2 Access Rules | 5 | TPX-1360
|  | IOIA-5346 Test (UAT & Prod): Display and Renewal Eligibility for Multiple Memberships in MyIIA | 5.5 | TPX-1110
|  | IOIA-5348 Test (UAT & Prod): Update Checkout Payment Processor Display Order and Labels | 5.5 | TPX-1583
|  | IOIA-5383 Apply primary-currency fallback for store payment method fees | 7.5 | TPX-1814
Mustafizur Rahman | 94 | IOIA-5263 Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 17.5
|  | IOIA-5321 Test (UAT & Prod): Implement NULL handling for the invalid creation_date | 1 | TPX-961
|  | IOIA-5322 Test (UAT & Prod): CCMS Reporting Admin Enhancement | 14 | TPX-1087
|  | IOIA-5323 Test (UAT & Prod): Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | 6 | TPX-1088
|  | IOIA-5327 Test (UAT & Prod): Update AI Certs Enrollment Validation and Handoff for Course 1 and Course 2 Access Rules | 7 | TPX-1360
|  | IOIA-5343 Test (UAT & Prod): CIA Practice Questions not showing Member Price on Website | 1 | TPX-1139
|  | IOIA-5350 CAD Commerce | 4.5 | TPX-1149
|  | IOIA-5352 Configure store currency And POS inheritance | 0.5 | TPX-1728
|  | IOIA-5353 Author and resolve product price overrides | 3.5 | TPX-1729
|  | IOIA-5354 Author And Resolve Pricing-Rule Price Overrides | 5.5 | TPX-1730
|  | IOIA-5355 Author And Resolve Discount Overrides | 1 | TPX-1731
|  | IOIA-5356 Author And Resolve Tier Price Overrides | 3.5 | TPX-1732
|  | IOIA-5357 Price And Allocate Bundles By Store | 5.5 | TPX-1733
|  | IOIA-5358 Use Store Base Currency Across Storefront And API | 0.5 | TPX-1734
|  | IOIA-5359 Keep Carts Separate By Store And Reject Stale Checkout | 0.5 | TPX-1735
|  | IOIA-5360 Convert Shipping Rates Before Adding Totals | 4.5 | TPX-1736
|  | IOIA-5361 Calculate Tax In The Correct Currency | 3.5 | TPX-1737
|  | IOIA-5362 Calculate Payment Fees And Filter Methods By Currency | 0.5 | TPX-1738
|  | IOIA-5363 Persist One Reconciled Order-Currency Snapshot | 0.5 | TPX-1739
|  | IOIA-5364 Read Old And New Orders Through One Money Service | 0.5 | TPX-1740
|  | IOIA-5365 Process Payments And Callbacks In Persisted Order Currency | 0.5 | TPX-1741
|  | IOIA-5366 Refund Exact Transaction-Currency Amounts | 0.5 | TPX-1742
|  | IOIA-5367 Complete POS Store Ordering | 0.5 | TPX-1743
|  | IOIA-5368 Create Quote/Invoice and convert them atomically | 0.5 | TPX-1744
|  | IOIA-5370 Test (UAT & Prod): Validate additional membership slot and ALN purchases after early group renewal | 11 | TPX-659
Total | 136.5 |  | 136.5

## Work logs
Author | Issue | Issue Summary | Work log started | Work log created | Work log time zone | Time spent | Work log comment | Client Reference
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-01 04:54 | 2026-10-05 05:26 | America/New_York | 1.5 | Communication with IIA, Daily Stand ups, Team Meeting
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-02 03:30 | 2026-10-05 05:32 | America/New_York | 2 | IIA DS and meetings
Foysal Rabbi | IOIA-5327 | Test (UAT & Prod): Update AI Certs Enrollment Validation and Handoff for Course 1 and Course 2 Access Rules | 2026-09-03 00:39 | 2026-10-05 05:41 | America/New_York | 5 | Test scenario, execution, and so on | TPX-1360
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-03 04:31 | 2026-10-05 05:33 | America/New_York | 1 | Communication with IIA, Daily Stand ups, Team Meeting
Foysal Rabbi | IOIA-5220 | Unexpected Failure During HubSpot Certification Synchronization | 2026-09-07 03:20 | 2026-10-05 05:53 | America/New_York | 1 | Requirement analysis, query, and others
Foysal Rabbi | IOIA-5234 | Webinar Teaser Card Dates | 2026-09-07 04:46 | 2026-10-05 05:48 | America/New_York | 1 | Issue: Try to reproduce | TPX-1162
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-08 05:12 | 2026-10-05 05:43 | America/New_York | 0.5 | Attend IIA DS
Foysal Rabbi | IOIA-5248 | Stripe charge discrepancy when quote is converted with different tax-rate address | 2026-09-09 02:03 | 2026-10-05 06:04 | America/New_York | 4 | Test script execution, and also gone through: Invoice, Note, Refund, Partial refund, Tax(HS Code), PDF settting, and so on | TPX-1378
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-09 05:13 | 2026-10-05 05:44 | America/New_York | 0.5 | IIA DS
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-10 05:13 | 2026-10-05 05:44 | America/New_York | 0.5 | IIA DS attend
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-14 04:28 | 2026-10-05 05:59 | America/New_York | 1.5 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-15 05:34 | 2026-10-05 06:08 | America/New_York | 0.5 | IIA meeting and DS
Foysal Rabbi | IOIA-5323 | Test (UAT & Prod): Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | 2026-09-16 04:41 | 2026-10-05 06:16 | America/New_York | 1.5 | Verify: Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | TPX-1088
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-16 05:47 | 2026-10-05 06:18 | America/New_York | 2 | Communication with IIA, Daily Stand ups, Team Meeting
Foysal Rabbi | IOIA-5348 | Test (UAT & Prod): Update Checkout Payment Processor Display Order and Labels | 2026-09-17 00:46 | 2026-10-05 06:17 | America/New_York | 5.5 | - Verify the configuration payment method and payment restriction - Verify the stripe in first order and PayPal in second order - Reported to Bell(Client) under this card with reproduce steps | TPX-1583
Foysal Rabbi | IOIA-5346 | Test (UAT & Prod): Display and Renewal Eligibility for Multiple Memberships in MyIIA | 2026-09-17 00:48 | 2026-10-05 06:20 | America/New_York | 5.5 | - Requirement analyze - Workflow in CRM - Workflow for the customer from the MyIIAUAT - Create an account from regier.iiauatext.org - Order place from POS [UAT] - Go through the test cases | TPX-1110
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-17 05:49 | 2026-10-05 06:20 | America/New_York | 0.5 | IIA DS
Foysal Rabbi | IOIA-5383 | Apply primary-currency fallback for store payment method fees | 2026-09-28 22:55 | 2026-10-05 06:26 | America/New_York | 7.5 | Analysis, test case design, and execution on the DEV | TPX-1814
Foysal Rabbi | IOIA-5262 | Communication with IIA, Daily Stand ups, Team Meeting - Foysal | 2026-09-30 05:23 | 2026-10-05 06:27 | America/New_York | 1 | Communication with IIA, Daily Stand ups, Team Meeting
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-01 09:54 | 2026-09-01 11:54 | America/New_York | 2 | DS QA process review meeting
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-02 09:00 | 2026-09-03 01:39 | America/New_York | 2 | IIA DS BS23 Demo : TPX - 1360 - AI Cert Enrollment Rules Update UAT QA processing overview meeting with the Allison
Mustafizur Rahman | IOIA-5327 | Test (UAT & Prod): Update AI Certs Enrollment Validation and Handoff for Course 1 and Course 2 Access Rules | 2026-09-03 03:00 | 2026-09-15 08:40 | America/New_York | 7 | requirement analysis test course 1 in UAT | TPX-1360
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-03 07:40 | 2026-09-15 08:41 | America/New_York | 1 | IIA DS
Mustafizur Rahman | IOIA-5321 | Test (UAT & Prod): Implement NULL handling for the invalid creation_date | 2026-09-07 07:41 | 2026-09-15 08:42 | America/New_York | 1 | requirement analysis | TPX-961
Mustafizur Rahman | IOIA-5322 | Test (UAT & Prod): CCMS Reporting Admin Enhancement | 2026-09-07 07:42 | 2026-09-15 08:42 | America/New_York | 1 | requirement analysis | TPX-1087
Mustafizur Rahman | IOIA-5323 | Test (UAT & Prod): Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | 2026-09-07 07:42 | 2026-09-15 08:43 | America/New_York | 1 | requirement analysis | TPX-1088
Mustafizur Rahman | IOIA-5343 | Test (UAT & Prod): CIA Practice Questions not showing Member Price on Website | 2026-09-07 08:00 | 2026-09-15 09:00 | America/New_York | 1 | requirement analysis | TPX-1139
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-09 03:30 | 2026-09-15 01:13 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-10 06:00 | 2026-09-15 01:13 | America/New_York | 1 | IIA DS
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-14 05:00 | 2026-09-15 01:16 | America/New_York | 1.5 | DS QA team blocker discussion with Eric
Mustafizur Rahman | IOIA-5322 | Test (UAT & Prod): CCMS Reporting Admin Enhancement | 2026-09-15 06:00 | 2026-09-16 01:19 | America/New_York | 4.5 | KT about CRM Site overview according to requirements | TPX-1087
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-15 09:00 | 2026-09-16 01:14 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-16 05:30 | 2026-09-17 01:49 | America/New_York | 1 | IIA DS
Mustafizur Rahman | IOIA-5322 | Test (UAT & Prod): CCMS Reporting Admin Enhancement | 2026-09-17 05:00 | 2026-09-18 01:23 | America/New_York | 5 | account creation test script creation test execution | TPX-1087
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-17 09:55 | 2026-09-17 10:25 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5322 | Test (UAT & Prod): CCMS Reporting Admin Enhancement | 2026-09-18 06:14 | 2026-09-18 09:45 | America/New_York | 3.5 | completed testing the feature Tested edited role scenarios Tested deleted role scenario | TPX-1087
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-18 09:15 | 2026-09-18 09:45 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5370 | Test (UAT & Prod): Validate additional membership slot and ALN purchases after early group renewal | 2026-09-21 08:30 | 2026-09-22 03:29 | America/New_York | 6 | Req Analysis, Feature understanding and Account Creation | TPX-659
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-21 09:00 | 2026-09-22 01:30 | America/New_York | 1 | IIA DS
Mustafizur Rahman | IOIA-5350 | CAD Commerce | 2026-09-22 02:50 | 2026-09-25 04:51 | America/New_York | 2 | local setup | TPX-1149
Mustafizur Rahman | IOIA-5370 | Test (UAT & Prod): Validate additional membership slot and ALN purchases after early group renewal | 2026-09-22 04:30 | 2026-09-23 01:20 | America/New_York | 5 | test complete | TPX-659
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-22 05:00 | 2026-09-23 01:16 | America/New_York | 1 | IIA DS
Mustafizur Rahman | IOIA-5350 | CAD Commerce | 2026-09-23 04:24 | 2026-09-25 04:55 | America/New_York | 0.5 | Checking requirement for test case preparation | TPX-1149
Mustafizur Rahman | IOIA-5323 | Test (UAT & Prod): Validation: Immediate Update for Global Pricing - Remove discounts from products on excel with N as the Global Pricing (Y/N) field. | 2026-09-23 09:30 | 2026-09-24 01:28 | America/New_York | 5 | completed testing feature | TPX-1088
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-23 10:30 | 2026-09-24 01:26 | America/New_York | 2.5 | IIA DS - 30m KT with Shahin vai about CAD - 2h
Mustafizur Rahman | IOIA-5355 | Author And Resolve Discount Overrides | 2026-09-24 03:47 | 2026-09-25 04:48 | America/New_York | 1 | test case writing | TPX-1731
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-24 04:00 | 2026-09-25 01:37 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5352 | Configure store currency And POS inheritance | 2026-09-24 04:16 | 2026-09-25 04:47 | America/New_York | 0.5 | test case writing | TPX-1728
Mustafizur Rahman | IOIA-5357 | Price And Allocate Bundles By Store | 2026-09-24 04:16 | 2026-09-25 04:47 | America/New_York | 0.5 | test case writing | TPX-1733
Mustafizur Rahman | IOIA-5353 | Author and resolve product price overrides | 2026-09-24 04:17 | 2026-09-25 04:47 | America/New_York | 0.5 | test case writing | TPX-1729
Mustafizur Rahman | IOIA-5354 | Author And Resolve Pricing-Rule Price Overrides | 2026-09-24 04:17 | 2026-09-25 04:48 | America/New_York | 0.5 | test case writing | TPX-1730
Mustafizur Rahman | IOIA-5356 | Author And Resolve Tier Price Overrides | 2026-09-24 04:18 | 2026-09-25 04:48 | America/New_York | 0.5 |  | TPX-1732
Mustafizur Rahman | IOIA-5361 | Calculate Tax In The Correct Currency | 2026-09-25 01:30 | 2026-09-28 02:01 | America/New_York | 0.5 | test case preparation | TPX-1737
Mustafizur Rahman | IOIA-5359 | Keep Carts Separate By Store And Reject Stale Checkout | 2026-09-25 02:30 | 2026-09-28 02:01 | America/New_York | 0.5 | test case preparation | TPX-1735
Mustafizur Rahman | IOIA-5360 | Convert Shipping Rates Before Adding Totals | 2026-09-25 02:30 | 2026-09-28 02:01 | America/New_York | 0.5 | test case preparation | TPX-1736
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-25 03:00 | 2026-09-28 02:02 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5363 | Persist One Reconciled Order-Currency Snapshot | 2026-09-25 03:00 | 2026-09-28 02:01 | America/New_York | 0.5 |  | TPX-1739
Mustafizur Rahman | IOIA-5362 | Calculate Payment Fees And Filter Methods By Currency | 2026-09-25 04:30 | 2026-09-28 02:01 | America/New_York | 0.5 | test case preparation | TPX-1738
Mustafizur Rahman | IOIA-5358 | Use Store Base Currency Across Storefront And API | 2026-09-25 05:00 | 2026-09-28 02:00 | America/New_York | 0.5 | test case preparation | TPX-1734
Mustafizur Rahman | IOIA-5364 | Read Old And New Orders Through One Money Service | 2026-09-25 07:00 | 2026-09-28 02:02 | America/New_York | 0.5 | test case preparation | TPX-1740
Mustafizur Rahman | IOIA-5353 | Author and resolve product price overrides | 2026-09-27 06:00 | 2026-09-28 02:08 | America/New_York | 3 | executed test cases | TPX-1729
Mustafizur Rahman | IOIA-5356 | Author And Resolve Tier Price Overrides | 2026-09-27 06:30 | 2026-09-28 02:08 | America/New_York | 3 | executed test cases | TPX-1732
Mustafizur Rahman | IOIA-5354 | Author And Resolve Pricing-Rule Price Overrides | 2026-09-27 07:00 | 2026-09-28 02:09 | America/New_York | 2 | executed test cases | TPX-1730
Mustafizur Rahman | IOIA-5367 | Complete POS Store Ordering | 2026-09-28 02:30 | 2026-09-29 01:32 | America/New_York | 0.5 | test case writing | TPX-1743
Mustafizur Rahman | IOIA-5366 | Refund Exact Transaction-Currency Amounts | 2026-09-28 03:00 | 2026-09-29 01:30 | America/New_York | 0.5 | test case writing | TPX-1742
Mustafizur Rahman | IOIA-5368 | Create Quote/Invoice and convert them atomically | 2026-09-28 04:00 | 2026-09-29 01:32 | America/New_York | 0.5 | test case writing | TPX-1744
Mustafizur Rahman | IOIA-5360 | Convert Shipping Rates Before Adding Totals | 2026-09-28 06:00 | 2026-09-29 01:33 | America/New_York | 1 | started testing the feature | TPX-1736
Mustafizur Rahman | IOIA-5365 | Process Payments And Callbacks In Persisted Order Currency | 2026-09-28 06:30 | 2026-09-29 01:29 | America/New_York | 0.5 | test case writing | TPX-1741
Mustafizur Rahman | IOIA-5350 | CAD Commerce | 2026-09-28 07:00 | 2026-09-29 01:32 | America/New_York | 2 | end to end testing | TPX-1149
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-28 07:30 | 2026-09-29 01:34 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5354 | Author And Resolve Pricing-Rule Price Overrides | 2026-09-28 08:00 | 2026-09-29 01:28 | America/New_York | 3 | test execution | TPX-1730
Mustafizur Rahman | IOIA-5360 | Convert Shipping Rates Before Adding Totals | 2026-09-29 05:00 | 2026-09-30 01:32 | America/New_York | 3 | completed test | TPX-1736
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-29 06:00 | 2026-09-30 01:24 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5357 | Price And Allocate Bundles By Store | 2026-09-29 07:00 | 2026-09-30 01:33 | America/New_York | 1.5 | discussion about the feature started testing the feature | TPX-1733
Mustafizur Rahman | IOIA-5361 | Calculate Tax In The Correct Currency | 2026-09-29 08:00 | 2026-09-30 01:32 | America/New_York | 3 | completed test | TPX-1737
Mustafizur Rahman | IOIA-5263 | Communication with IIA, Daily Stand ups, Team Meeting - Mustafizur | 2026-09-30 07:30 | 2026-10-01 01:25 | America/New_York | 0.5 | IIA DS
Mustafizur Rahman | IOIA-5357 | Price And Allocate Bundles By Store | 2026-09-30 08:30 | 2026-10-01 01:26 | America/New_York | 3.5 | dev test complete | TPX-1733