## Report
From |  | 2026-09-01 |  | To |  | 2026-09-29
Projects |  | FloraFire nopStation
Time Zone |  | Current User
Generated on |  | 2026-09-29T08:40:06-04:00
Report Time Format |  | Hours
Work logs Time Format |  | Hours
Issue | Total Issue | Summary | Total Summary | Status | Total Status
FFN-2044 | 6 | FFN-2044 WBS Additional - Fulfilling Store | 6 | UAT | 6
FFN-2500 | 8 | FFN-2500 WBS Additional- Printing scheduler- Development | 8 | QA Failed | 8
FFN-2542 | 2 | FFN-2542 WBS Additional-Wire Service Message- Cancel, Cancel, Confirm cancel, order Deny, Deny Cancel- Development | 2 | QA | 2
FFN-2589 | 2.5 | FFN-2589 WBS Additional- Internet Order- Development | 2.5 | QA | 2.5
FFN-2591 | 6 | FFN-2591 WBS Additional- Unpaid Order Processing- Development | 6 | UAT | 6
FFN-2592 | 3 | FFN-2592 WBS Additional- Unpaid Order Processing- QA | 3 | UAT | 3
FFN-2610 | 4 | FFN-2610 UAT 4.0 CR - Implement fallback logic to use previous Delivery Calendar setup if current date is unconfigured | 4 | To Do | 4
FFN-2613 | 2 | FFN-2613 UAT 4.0 Issue - Validate Customer Email and Prevent Printing When "Email Customer Copy" Is Selected | 2 | UAT | 2
FFN-2614 | 0.5 | FFN-2614 UAT 4.0 Feedback - Consolidate Same-Recipient Items into a Single Sub Order and Work Order | 0.5 | QA Failed | 0.5
FFN-2615 | 0.5 | FFN-2615 UAT 4.0 Feedback - Reformat Customer Order Copy Layout for Standardized Address and Card Message Structure | 0.5 | UAT | 0.5
FFN-2620 | 14 | FFN-2620 UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 14 | Code Review | 14
FFN-2622 | 5.5 | FFN-2622 UAT 4.0 Issue - Incorrect Date Shift When Selecting Single Date in Delivery Calender | 5.5 | To Do | 5.5
FFN-2625 | 1 | FFN-2625 UAT 4.0 Issue - Incorrect Handling of Will Call Recipient Details, Card Message Auto-Population, and Pickup Field Timing | 1 | UAT | 1
FFN-2641 | 8.5 | FFN-2641 Packagelane – Security & Infrastructure Architecture Assessment | 8.5 | To Do | 8.5
FFN-2644 | 5 | FFN-2644 UAT 4.0 QA and Testing | 5 | In Progress | 5
FFN-2667 | 1 | FFN-2667 WBS Additional- Delivery Types- Fringe - Development | 1 | QA Failed | 1
FFN-2683 | 2 | FFN-2683 Integrate Integration Test in CI/CD Pipeline | 2 | To Do | 2
FFN-2794 | 1 | FFN-2794 Clear Cache from Admin- QA | 1 | Done | 1
FFN-2805 | 12 | FFN-2805 WBS Additional- Invoice Auto Generation- Development | 12 | Done | 12
FFN-2806 | 2 | FFN-2806 WBS Additional- Invoice Auto Generation- QA | 2 | Done | 2
FFN-2830 | 28 | FFN-2830 Delivery App - Internal Issue Fixing - Development | 28 | Done | 28
FFN-2831 | 8 | FFN-2831 Delivery App - Internal Issue Fixing - QA | 8 | Done | 8
FFN-2840 | 2 | FFN-2840 Delivery App - Refresh Token Implementation in Web - QA | 2 | Done | 2
FFN-2842 | 15.5 | FFN-2842 CR- Checkout Box Order and Release Flow Implementation- Development | 15.5 | QA | 15.5
FFN-2843 | 2 | FFN-2843 CR- Checkout Box Order and Release Flow Implementation- QA | 2 | To Do | 2
FFN-2845 | 39 | FFN-2845 Sprint 43- Project Management- Atashi | 39 | Done | 39
FFN-2846 | 19 | FFN-2846 Sprint 43- Project Management- Tanvir | 19 | Done | 19
FFN-2849 | 8 | FFN-2849 Sprint 43- Code Review- Tanvir | 8 | Done | 8
FFN-2851 | 4.5 | FFN-2851 Sprint 43- Code Review- Rajib | 4.5 | Done | 4.5
FFN-2854 | 4 | FFN-2854 Issue- Batch Payment Issue Fixing- Development | 4 | To Do | 4
FFN-2857 | 8.5 | FFN-2857 DAP2-Issue- Packagelane Mobile Responsiveness- Development | 8.5 | Done | 8.5
FFN-2858 | 1 | FFN-2858 DAP2-Issue- Packagelane Mobile Responsiveness- QA | 1 | Done | 1
FFN-2863 | 46.5 | FFN-2863 WBS Additional- GL Setup functionalities Configuration- Development | 46.5 | To Do | 46.5
FFN-2865 | 26.5 | FFN-2865 Internal- Wire Service Testing- Nayef | 26.5 | In Progress | 26.5
FFN-2866 | 33.5 | FFN-2866 Internal- Wire Service Testing- Rajib | 33.5 | Code Review | 33.5
FFN-2870 | 1 | FFN-2870 Issue- Password Sync - QA | 1 | Done | 1
FFN-2875 | 3 | FFN-2875 Agent Testing - Driver Module | 3 | Done | 3
FFN-2876 | 3 | FFN-2876 Agent Testing - Order Module | 3 | Done | 3
FFN-2877 | 3 | FFN-2877 Agent Testing - Trip Module | 3 | Done | 3
FFN-2878 | 4 | FFN-2878 Weekly Task Update Meeting- 02 September 2026 | 4 | Done | 4
FFN-2880 | 8 | FFN-2880 WBS Additional- To Be Expired Category Implementation in Checkout box- Development | 8 | Code Review | 8
FFN-2884 | 4 | FFN-2884 Delivery App v3.2 UAT Issue - Paystri Field Toast Validation | 4 | Done | 4
FFN-2885 | 4 | FFN-2885 Delivery App v3.2 UAT CR - Reactivation Fee Reinstation | 4 | Done | 4
FFN-2886 | 1 | FFN-2886 Delivery App v3.2 UAT Issue - Florafire user approval issue | 1 | Done | 1
FFN-2887 | 2 | FFN-2887 Delivery App v3.2 UAT CR - Delivery Date Column type needs to be changed from Text to Custom | 2 | Done | 2
FFN-2888 | 3 | FFN-2888 Delivery App v3.2 UAT CR - Address validation for orders from Trip page | 3 | Done | 3
FFN-2889 | 4 | FFN-2889 Delivery App v3.2 UAT Feedback - QA | 4 | Done | 4
FFN-2890 | 6 | FFN-2890 Delivery App v3.2 UAT Issue - Subscription page UI fix | 6 | Done | 6
FFN-2891 | 16 | FFN-2891 Packagelane Load Testing | 16 | Done | 16
FFN-2892 | 1.5 | FFN-2892 Weekly Task Update Meeting- 09 September 2026 | 1.5 | Done | 1.5
FFN-2893 | 35 | FFN-2893 WBS Additional- Delivery Types- Pool - Development | 35 | Code Review | 35
FFN-2894 | 9.5 | FFN-2894 Packagelane Frontdoor Integration | 9.5 | To Do | 9.5
FFN-2895 | 4 | FFN-2895 Packagelane Migration to Linux App Service | 4 | To Do | 4
FFN-2896 | 16 | FFN-2896 Internal-Wire Service Shop Sync and Shop Search for Recipient Address | 16 | QA | 16
FFN-2897 | 68.5 | FFN-2897 Sprint 44- Project Management | 68.5 | To Do | 68.5
FFN-2898 | 9 | FFN-2898 Sprint 44- Weekly Task Update Meeting | 9 | To Do | 9
FFN-2899 | 9.5 | FFN-2899 Sprint Review and Planning Meeting | 9.5 | Done | 9.5
FFN-2900 | 3.5 | FFN-2900 Sprint 44- QA Miscellaneous Activities | 3.5 | To Do | 3.5
FFN-2909 | 3.5 | FFN-2909 WBS Additional- Delivery Types- Ship - QA | 3.5 | To Do | 3.5
FFN-2910 | 3.5 | FFN-2910 WBS Additional- Delivery Types- Fringe - QA | 3.5 | To Do | 3.5
FFN-2913 | 5 | FFN-2913 WBS Additional - Implement Shipping Slots and Integrate with Shipping Order Type | 5 | QA Failed | 5
FFN-2914 | 4 | FFN-2914 WBS Additional- MAS API Portal & Integration - Requirement Analysis | 4 | To Do | 4
FFN-2915 | 8 | FFN-2915 PackageLane Prototype Creation | 8 | To Do | 8
FFN-2918 | 8 | FFN-2918 WBS Additional- GL Setup functionalities implementation(CRUD) - Development | 8 | QA | 8
FFN-2921 | 14 | FFN-2921 WBS Additional- Run GL Report & Show in List- Development | 14 | Code Review | 14
FFN-2927 | 3 | FFN-2927 Agent Testing - Subscription Module | 3 | To Do | 3
Total | 600 |  | 600 |  | 600

## Work logs
Author | Issue | Issue Summary | Work log started | Work log created | Work log time zone | Time spent | Work log comment
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-01 11:30 | 2026-09-03 02:42 | America/New_York | 1 | Management
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-02 11:30 | 2026-09-03 02:43 | America/New_York | 6.5 | Client meeting Requirement analysis User story update for checkout box Management
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-03 11:30 | 2026-09-10 02:47 | America/New_York | 6.5 | Requirement analysis for General ledger and employee setup from last meeting Backlog grooming and track task progress for current sprint Management
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-07 11:30 | 2026-09-12 23:44 | America/New_York | 4 | Backlog grooming Remaining task list update GL documentaion
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-08 11:30 | 2026-09-12 23:41 | America/New_York | 6 | GL Requirement analysis Internal discussion Send Meeting Agenda to the client R & D on Debit credit balancing
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-09 11:30 | 2026-09-12 23:39 | America/New_York | 6.5 | Client meeting Sprint review and planning Internal discussion on GL Requirement analysis and questionnaire prepared for GL
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-10 11:30 | 2026-09-12 23:37 | America/New_York | 5.5 | Master data update GL Requirement Analysis Internal meeting for task discussion for next Sprint Management
Atashi Mani Ghosh | FFN-2845 | Sprint 43- Project Management- Atashi | 2026-09-11 11:30 | 2026-09-11 10:06 | America/New_York | 3 | Sprint review and planning meeting Backlog grooming Master data update Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-14 11:30 | 2026-09-21 02:35 | America/New_York | 4 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-15 11:30 | 2026-09-21 02:36 | America/New_York | 5 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-18 11:30 | 2026-09-21 02:37 | America/New_York | 6 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-22 11:30 | 2026-09-28 02:35 | America/New_York | 5 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-23 11:30 | 2026-09-28 02:35 | America/New_York | 5 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-24 11:30 | 2026-09-28 02:36 | America/New_York | 5 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-25 11:30 | 2026-09-28 02:36 | America/New_York | 5 | Management
Atashi Mani Ghosh | FFN-2897 | Sprint 44- Project Management | 2026-09-29 08:00 | 2026-09-29 08:37 | America/New_York | 1 | test
Mahfuzur Rahman | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-01 12:00 | 2026-09-02 02:37 | America/New_York | 7 | Miscellenous issue fixes and webhook issue check
Mahfuzur Rahman | FFN-2857 | DAP2-Issue- Packagelane Mobile Responsiveness- Development | 2026-09-02 18:53 | 2026-09-03 02:24 | America/New_York | 7.5 | fixed responsiveness system wide
Mahfuzur Rahman | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-03 21:00 | 2026-09-03 09:31 | America/New_York | 8 | Fixed here map api key loading issue and trip module internal issue feedback
Mahfuzur Rahman | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-10 19:24 | 2026-09-11 01:55 | America/New_York | 6.5 | Logo in forget password page, Driver status on driver list page, Remove occasion from order list, Add trip, order number, residence in order list, Add external trip number in trip list page search. And other deployment related check.
Mahfuzur Rahman | FFN-2857 | DAP2-Issue- Packagelane Mobile Responsiveness- Development | 2026-09-10 22:00 | 2026-09-11 01:52 | America/New_York | 1 | Reviewed responsiveness, merge conflict resolve, uat review and hot fix for trip’s selected order address valiation.
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-11 08:38 | 2026-09-11 09:38 | America/New_York | 1 | KT with team
Mahfuzur Rahman | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-11 22:00 | 2026-09-11 09:37 | America/New_York | 4.5 | * Admin dashboard restructure and removal of metrics * Updated driver AvailabilityStatus
Mahfuzur Rahman | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-11 22:00 | 2026-09-11 09:38 | America/New_York | 1.5 | Sprint planning meeting.
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-14 10:00 | 2026-09-15 02:25 | America/New_York | 7.5 | * Collaborated with QA for preparing test cases. * Prepare planning for implementation. * Implemented outgoing flow. * Implemented POS page functionality for incoming.
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-15 11:30 | 2026-09-16 02:30 | America/New_York | 7.5 | Implemented the incoming order and delivery control quick order creation.
Mahfuzur Rahman | FFN-2898 | Sprint 44- Weekly Task Update Meeting | 2026-09-16 21:00 | 2026-09-17 02:50 | America/New_York | 3 | Client demo and preparation for pool delivery
Mahfuzur Rahman | FFN-2613 | UAT 4.0 Issue - Validate Customer Email and Prevent Printing When "Email Customer Copy" Is Selected | 2026-09-16 22:00 | 2026-09-17 02:18 | America/New_York | 0.5 | Investigate issue for print not working and email not queueing
Mahfuzur Rahman | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-16 22:00 | 2026-09-17 02:19 | America/New_York | 0.5 | Fix impersonation issue for refresh token
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-16 22:20 | 2026-09-17 02:20 | America/New_York | 4 | Review the whole pool flow and team demo.
Mahfuzur Rahman | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-16 23:21 | 2026-09-17 02:21 | America/New_York |  | Client demo and preparation for pool delivery
Mahfuzur Rahman | FFN-2613 | UAT 4.0 Issue - Validate Customer Email and Prevent Printing When "Email Customer Copy" Is Selected | 2026-09-17 13:30 | 2026-09-18 01:45 | America/New_York | 1 | Print and email issue fix.
Mahfuzur Rahman | FFN-2614 | UAT 4.0 Feedback - Consolidate Same-Recipient Items into a Single Sub Order and Work Order | 2026-09-17 14:00 | 2026-09-18 01:46 | America/New_York | 0.5 | Added email and print functionalities for other options.
Mahfuzur Rahman | FFN-2615 | UAT 4.0 Feedback - Reformat Customer Order Copy Layout for Standardized Address and Card Message Structure | 2026-09-17 18:00 | 2026-09-18 01:46 | America/New_York | 0.5 | Added email and print functionalities for other options.
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-17 21:17 | 2026-09-18 01:48 | America/New_York | 5.5 | Updated incoming pool delivery client feedback: - Changed description to optional * Removed payment requirement * Removed checkout box review
Mahfuzur Rahman | FFN-2622 | UAT 4.0 Issue - Incorrect Date Shift When Selecting Single Date in Delivery Calender | 2026-09-18 04:54 | 2026-09-18 09:55 | America/New_York | 5 | Calender display mismatch fix
Mahfuzur Rahman | FFN-2667 | WBS Additional- Delivery Types- Fringe - Development | 2026-09-18 09:04 | 2026-09-18 10:05 | America/New_York | 1 | Investigate issue related to fringe delivery not populating to delivery control
Mahfuzur Rahman | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-22 11:30 | 2026-09-23 02:15 | America/New_York | 3.5 | PR feedback and db structure upgradation
Mustafizur Rahman | FFN-2875 | Agent Testing - Driver Module | 2026-09-01 09:20 | 2026-09-01 11:20 | America/New_York | 3 | completed the feature
Mustafizur Rahman | FFN-2876 | Agent Testing - Order Module | 2026-09-01 09:20 | 2026-09-01 11:20 | America/New_York | 3 | completed the feature
Mustafizur Rahman | FFN-2831 | Delivery App - Internal Issue Fixing - QA | 2026-09-02 00:04 | 2026-09-03 02:05 | America/New_York | 2 | checked issues
Mustafizur Rahman | FFN-2877 | Agent Testing - Trip Module | 2026-09-02 05:00 | 2026-09-03 02:06 | America/New_York | 3 | completed trip module
Mustafizur Rahman | FFN-2878 | Weekly Task Update Meeting- 02 September 2026 | 2026-09-02 09:27 | 2026-09-02 10:27 | America/New_York | 1 | client meeting
Mustafizur Rahman | FFN-2889 | Delivery App v3.2 UAT Feedback - QA | 2026-09-07 19:00 | 2026-09-07 13:03 | America/New_York | 4 | 1. Prepared Jira card 2. Discuss work scope with dev 3. Tested in dev 4. Tested in uat
Mustafizur Rahman | FFN-2891 | Packagelane Load Testing | 2026-09-09 17:55 | 2026-09-10 01:56 | America/New_York | 8 | Plan about the structure about the project for load test
Mustafizur Rahman | FFN-2891 | Packagelane Load Testing | 2026-09-10 17:41 | 2026-09-11 00:42 | America/New_York | 4 | prepared load test data and script
Mustafizur Rahman | FFN-2831 | Delivery App - Internal Issue Fixing - QA | 2026-09-10 21:46 | 2026-09-11 00:46 | America/New_York | 3 | tested
Mustafizur Rahman | FFN-2831 | Delivery App - Internal Issue Fixing - QA | 2026-09-11 05:07 | 2026-09-11 08:08 | America/New_York | 3 | tested resolved features
Mustafizur Rahman | FFN-2891 | Packagelane Load Testing | 2026-09-11 06:28 | 2026-09-11 09:28 | America/New_York | 1 | implementing load test script
Mustafizur Rahman | FFN-2858 | DAP2-Issue- Packagelane Mobile Responsiveness- QA | 2026-09-11 07:14 | 2026-09-11 08:14 | America/New_York | 1 | tested resolved feedback
Mustafizur Rahman | FFN-2592 | WBS Additional- Unpaid Order Processing- QA | 2026-09-11 08:32 | 2026-09-11 09:32 | America/New_York | 1 | tested the feature
Mustafizur Rahman | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-11 08:49 | 2026-09-11 10:49 | America/New_York | 2 | sprint meeting
Mustafizur Rahman | FFN-2794 | Clear Cache from Admin- QA | 2026-09-14 03:07 | 2026-09-14 04:08 | America/New_York | 1 | tested feature
Mustafizur Rahman | FFN-2870 | Issue- Password Sync - QA | 2026-09-14 04:41 | 2026-09-14 05:41 | America/New_York | 1 | tested
Mustafizur Rahman | FFN-2840 | Delivery App - Refresh Token Implementation in Web - QA | 2026-09-14 05:52 | 2026-09-14 06:52 | America/New_York | 2 | tested
Mustafizur Rahman | FFN-2910 | WBS Additional- Delivery Types- Fringe - QA | 2026-09-14 14:00 | 2026-09-15 03:10 | America/New_York | 1.5 | tested feature
Mustafizur Rahman | FFN-2909 | WBS Additional- Delivery Types- Ship - QA | 2026-09-14 15:30 | 2026-09-15 03:10 | America/New_York | 1.5 | tested feature
Mustafizur Rahman | FFN-2900 | Sprint 44- QA Miscellaneous Activities | 2026-09-15 16:30 | 2026-09-16 01:37 | America/New_York | 1 | internal discussion
Mustafizur Rahman | FFN-2644 | UAT 4.0 QA and Testing | 2026-09-15 23:36 | 2026-09-16 01:37 | America/New_York | 2 | tested resolved feature
Mustafizur Rahman | FFN-2898 | Sprint 44- Weekly Task Update Meeting | 2026-09-16 01:00 | 2026-09-17 02:04 | America/New_York | 1 | client meeting
Mustafizur Rahman | FFN-2644 | UAT 4.0 QA and Testing | 2026-09-16 22:59 | 2026-09-17 02:07 | America/New_York | 3 | tested resolved feature
Mustafizur Rahman | FFN-2891 | Packagelane Load Testing | 2026-09-16 23:16 | 2026-09-17 02:17 | America/New_York | 3 | continue implementation
Mustafizur Rahman | FFN-2592 | WBS Additional- Unpaid Order Processing- QA | 2026-09-17 07:07 | 2026-09-17 09:07 | America/New_York | 2 | tested the feature
Mustafizur Rahman | FFN-2900 | Sprint 44- QA Miscellaneous Activities | 2026-09-17 12:00 | 2026-09-18 01:24 | America/New_York | 0.5 | internal discussion
Mustafizur Rahman | FFN-2910 | WBS Additional- Delivery Types- Fringe - QA | 2026-09-18 22:39 | 2026-09-19 00:40 | America/New_York | 2 | tested feature
Mustafizur Rahman | FFN-2909 | WBS Additional- Delivery Types- Ship - QA | 2026-09-18 23:39 | 2026-09-19 00:39 | America/New_York | 1 | tested feature
Mustafizur Rahman | FFN-2900 | Sprint 44- QA Miscellaneous Activities | 2026-09-18 23:40 | 2026-09-19 00:40 | America/New_York | 1 | internal discussion
Mustafizur Rahman | FFN-2900 | Sprint 44- QA Miscellaneous Activities | 2026-09-21 16:30 | 2026-09-22 01:46 | America/New_York | 1 | internal discussion
Mustafizur Rahman | FFN-2806 | WBS Additional- Invoice Auto Generation- QA | 2026-09-24 23:28 | 2026-09-25 01:28 | America/New_York | 2 | tested
Mustafizur Rahman | FFN-2843 | CR- Checkout Box Order and Release Flow Implementation- QA | 2026-09-24 23:29 | 2026-09-25 01:29 | America/New_York | 2 | tested feature
Mustafizur Rahman | FFN-2927 | Agent Testing - Subscription Module | 2026-09-25 08:37 | 2026-09-25 11:37 | America/New_York | 3 | prepared subscription module test coverage and documentation
Mustafizur Rahman | FFN-2909 | WBS Additional- Delivery Types- Ship - QA | 2026-09-25 10:33 | 2026-09-25 11:33 | America/New_York | 1 | tested feature
Nayef Al Mahbub | FFN-2805 | WBS Additional- Invoice Auto Generation- Development | 2026-09-01 23:55 | 2026-09-07 05:56 | America/New_York | 6 | Refactored invoicing logic
Nayef Al Mahbub | FFN-2805 | WBS Additional- Invoice Auto Generation- Development | 2026-09-02 12:00 | 2026-09-07 05:58 | America/New_York | 3 | Complete refactoring invoicing. Move pdf generation to the backend.
Nayef Al Mahbub | FFN-2880 | WBS Additional- To Be Expired Category Implementation in Checkout box- Development | 2026-09-02 12:00 | 2026-09-07 06:00 | America/New_York | 3.5 | Created soon to be expired standing order template new category
Nayef Al Mahbub | FFN-2805 | WBS Additional- Invoice Auto Generation- Development | 2026-09-07 00:07 | 2026-09-08 03:08 | America/New_York | 3 | Add background worker for auto generation invoice
Nayef Al Mahbub | FFN-2885 | Delivery App v3.2 UAT CR - Reactivation Fee Reinstation | 2026-09-07 22:54 | 2026-09-08 02:54 | America/New_York | 4 | Complete implementation & testing of reactivation fee reinstation feature
Nayef Al Mahbub | FFN-2880 | WBS Additional- To Be Expired Category Implementation in Checkout box- Development | 2026-09-08 11:00 | 2026-09-10 09:46 | America/New_York | 4.5 | Complete soon to be expired standing order template category
Nayef Al Mahbub | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-08 23:20 | 2026-09-18 02:51 | America/New_York | 3.5 | Fixed wire service shop related issues
Nayef Al Mahbub | FFN-2892 | Weekly Task Update Meeting- 09 September 2026 | 2026-09-09 18:00 | 2026-09-10 09:32 | America/New_York | 0.5 | Attend client meeting
Nayef Al Mahbub | FFN-2896 | Internal-Wire Service Shop Sync and Shop Search for Recipient Address | 2026-09-09 18:31 | 2026-09-14 02:02 | America/New_York | 7.5 | Refactor shop sync code. Instead of sequential processing, used parallelism.
Nayef Al Mahbub | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-10 01:04 | 2026-09-14 02:04 | America/New_York | 1 | Internal discussion about pool delivery type & review user story
Nayef Al Mahbub | FFN-2896 | Internal-Wire Service Shop Sync and Shop Search for Recipient Address | 2026-09-10 19:02 | 2026-09-14 02:04 | America/New_York | 7 | Complete shop sync issue fixing & improve performance for shop sync
Nayef Al Mahbub | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-11 00:57 | 2026-09-14 01:57 | America/New_York | 2 | Attend sprint planning & review meeting
Nayef Al Mahbub | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-11 00:59 | 2026-09-14 02:00 | America/New_York | 1 | KT regarding pool delivery type
Nayef Al Mahbub | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-11 21:05 | 2026-09-14 02:06 | America/New_York | 5 | Improving shop searching algorithm for a specific recipient
Nayef Al Mahbub | FFN-2500 | WBS Additional- Printing scheduler- Development | 2026-09-14 18:36 | 2026-09-18 02:38 | America/New_York | 8 | Investigate printing scheduler issue. Fixed it, and tested locally.
Nayef Al Mahbub | FFN-2842 | CR- Checkout Box Order and Release Flow Implementation- Development | 2026-09-15 18:40 | 2026-09-18 02:41 | America/New_York | 8 | Delivery status & order status issue fix. Centralize status related logic
Nayef Al Mahbub | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-16 01:41 | 2026-09-18 02:43 | America/New_York | 1 | Internal meeting, demo regarding Pool order
Nayef Al Mahbub | FFN-2914 | WBS Additional- MAS API Portal & Integration - Requirement Analysis | 2026-09-16 01:43 | 2026-09-18 02:43 | America/New_York | 1 | Internal meeting regarding MAS direct network
Nayef Al Mahbub | FFN-2842 | CR- Checkout Box Order and Release Flow Implementation- Development | 2026-09-16 20:45 | 2026-09-18 02:45 | America/New_York | 6 | Complete delivery status issue fixed, created PR & resolved PR feedbacks
Nayef Al Mahbub | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-17 18:46 | 2026-09-18 02:46 | America/New_York | 8 | Refactor shop searching functionality in order entry page, improved shop searching feature
Nayef Al Mahbub | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-18 00:20 | 2026-09-24 05:21 | America/New_York | 5 | Continue working on wire service testing
Nayef Al Mahbub | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-18 11:00 | 2026-09-24 05:20 | America/New_York | 1 | Code review
Nayef Al Mahbub | FFN-2897 | Sprint 44- Project Management | 2026-09-18 16:00 | 2026-09-24 05:20 | America/New_York | 2 | Review meeting
Nayef Al Mahbub | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-22 12:00 | 2026-09-24 05:33 | America/New_York | 4 | Fixed wire service related issue
Nayef Al Mahbub | FFN-2893 | WBS Additional- Delivery Types- Pool - Development | 2026-09-22 12:00 | 2026-09-24 05:22 | America/New_York | 2 | Code review
Nayef Al Mahbub | FFN-2898 | Sprint 44- Weekly Task Update Meeting | 2026-09-22 18:00 | 2026-09-24 05:41 | America/New_York | 1.5 | Attend client meeting
Nayef Al Mahbub | FFN-2589 | WBS Additional- Internet Order- Development | 2026-09-23 17:00 | 2026-09-24 05:28 | America/New_York | 2 | Completed internet order & created PR
Nayef Al Mahbub | FFN-2044 | WBS Additional - Fulfilling Store | 2026-09-23 23:30 | 2026-09-24 05:30 | America/New_York | 6 | Refactor fulfilling store related logic, fix store related issues
Rajib Sarker | FFN-2625 | UAT 4.0 Issue - Incorrect Handling of Will Call Recipient Details, Card Message Auto-Population, and Pickup Field Timing | 2026-09-01 11:00 | 2026-09-02 01:35 | America/New_York | 1 | * Recipient name carry on add new form array in order personalization
Rajib Sarker | FFN-2851 | Sprint 43- Code Review- Rajib | 2026-09-01 13:30 | 2026-09-02 01:37 | America/New_York | 1.5 | * Code review
Rajib Sarker | FFN-2542 | WBS Additional-Wire Service Message- Cancel, Cancel, Confirm cancel, order Deny, Deny Cancel- Development | 2026-09-01 15:30 | 2026-09-02 01:41 | America/New_York | 2 | * Resolved issues on wire service messages functionality
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-01 16:00 | 2026-09-02 01:41 | America/New_York | 3.5 | * Dev wire service credentials setup in different tenants * Wire service message testing
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-02 11:00 | 2026-09-07 01:03 | America/New_York | 3.5 | * Wire service - TF functionalities testing in dev environment
Rajib Sarker | FFN-2620 | UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 2026-09-02 16:00 | 2026-09-07 00:59 | America/New_York | 2 | * Analyze the order creation process, individual payment with cash register selection for different generic users
Rajib Sarker | FFN-2878 | Weekly Task Update Meeting- 02 September 2026 | 2026-09-02 18:00 | 2026-09-07 00:58 | America/New_York | 1.5 | * Client meeting regarding generic user creation
Rajib Sarker | FFN-2884 | Delivery App v3.2 UAT Issue - Paystri Field Toast Validation | 2026-09-07 11:00 | 2026-09-08 01:00 | America/New_York | 3 | * Fixed paystri credit card payment unnecessary toaster messages and enable button click for tokenization * PR created on that
Rajib Sarker | FFN-2890 | Delivery App v3.2 UAT Issue - Subscription page UI fix | 2026-09-07 13:00 | 2026-09-08 01:01 | America/New_York | 1 | * Redesign the subscription page UI * PR created on that
Rajib Sarker | FFN-2851 | Sprint 43- Code Review- Rajib | 2026-09-07 14:30 | 2026-09-08 02:42 | America/New_York | 1 | * Code review
Rajib Sarker | FFN-2887 | Delivery App v3.2 UAT CR - Delivery Date Column type needs to be changed from Text to Custom | 2026-09-07 16:00 | 2026-09-08 01:01 | America/New_York | 2 | * Fixed the delivery date column format to custom format * PR created on that
Rajib Sarker | FFN-2886 | Delivery App v3.2 UAT Issue - Florafire user approval issue | 2026-09-07 19:00 | 2026-09-08 01:03 | America/New_York | 1 | * Fixed the issues on Packagelane user approval for sending email using email template * PR created on that
Rajib Sarker | FFN-2851 | Sprint 43- Code Review- Rajib | 2026-09-08 06:30 | 2026-09-10 02:16 | America/New_York | 1 | * Code review
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-08 11:00 | 2026-09-10 02:06 | America/New_York | 7 | * Go through with basic accounting, chart of accounts & convert different transaction into debit/credit * Analyze the general ledger client meeting * Sit with internal team regarding that
Rajib Sarker | FFN-2884 | Delivery App v3.2 UAT Issue - Paystri Field Toast Validation | 2026-09-10 11:00 | 2026-09-11 02:31 | America/New_York | 1 | * Fixed Paystri css issue
Rajib Sarker | FFN-2851 | Sprint 43- Code Review- Rajib | 2026-09-10 12:30 | 2026-09-11 02:32 | America/New_York | 1 | * Code review
Rajib Sarker | FFN-2890 | Delivery App v3.2 UAT Issue - Subscription page UI fix | 2026-09-10 14:00 | 2026-09-11 02:33 | America/New_York | 5 | * Redesign the Packagelane subscription UI design * PR created on that
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-11 11:00 | 2026-09-14 01:43 | America/New_York | 1 | * Analyze on general ledger
Rajib Sarker | FFN-2620 | UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 2026-09-11 12:00 | 2026-09-14 01:44 | America/New_York | 3 | * Worked on the generic users implementation
Rajib Sarker | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-11 14:30 | 2026-09-14 01:36 | America/New_York | 2 | * Sprint meeting
Rajib Sarker | FFN-2591 | WBS Additional- Unpaid Order Processing- Development | 2026-09-11 18:00 | 2026-09-14 01:38 | America/New_York | 1 | * Internal discussion regarding the unpaid order failure process.
Rajib Sarker | FFN-2620 | UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 2026-09-14 11:00 | 2026-09-15 01:53 | America/New_York | 6 | * Generic user created by check box * Generic employees defaults configuration * Generic employees order creation
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-14 19:30 | 2026-09-15 01:54 | America/New_York | 2 | * Attended on general ledger requirements gathering meeting
Rajib Sarker | FFN-2620 | UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 2026-09-15 11:00 | 2026-09-16 02:00 | America/New_York | 2 | * Removed existing generic role functionalities * PR created on that
Rajib Sarker | FFN-2591 | WBS Additional- Unpaid Order Processing- Development | 2026-09-15 14:00 | 2026-09-16 02:02 | America/New_York | 5 | * Fixed issues on unpaid order delivery status update * Order control sub order delivery status issues solved
Rajib Sarker | FFN-2913 | WBS Additional - Implement Shipping Slots and Integrate with Shipping Order Type | 2026-09-16 12:30 | 2026-09-17 01:46 | America/New_York | 0.5 | * Code review
Rajib Sarker | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-16 13:30 | 2026-09-17 01:45 | America/New_York | 0.5 | * Code review
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-16 14:00 | 2026-09-17 01:51 | America/New_York | 6 | * Gather knowledge about GL configuration * Understood the GL report
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-17 11:00 | 2026-09-18 01:46 | America/New_York | 6.5 | * Tested wire service general messages functionalities * Issues solved for MAS General Messages functionalities * Run audit for MAS, Teleflora messages functionalities and issues solved
Rajib Sarker | FFN-2613 | UAT 4.0 Issue - Validate Customer Email and Prevent Printing When "Email Customer Copy" Is Selected | 2026-09-17 18:00 | 2026-09-18 01:45 | America/New_York | 0.5 | * Code review
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-18 11:00 | 2026-09-21 01:36 | America/New_York | 7 | * Tested FTD and Bloomnet functionalities * Tested order outgoing functionalities
Rajib Sarker | FFN-2622 | UAT 4.0 Issue - Incorrect Date Shift When Selecting Single Date in Delivery Calender | 2026-09-18 12:00 | 2026-09-21 01:34 | America/New_York | 0.5 | * Code review
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-21 11:00 | 2026-09-22 01:57 | America/New_York | 8 | * Fixed wire service outgoing order creation issues * Fixed outgoing wire services messages functionalities
Rajib Sarker | FFN-2866 | Internal- Wire Service Testing- Rajib | 2026-09-22 11:00 | 2026-09-24 02:04 | America/New_York | 5 | * Wire service all message types testing and issues fixing
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-22 17:30 | 2026-09-24 02:05 | America/New_York | 2 | * Analysis the GL setup requirements * Attended on client meeting regarding GL requirements
Rajib Sarker | FFN-2921 | WBS Additional- Run GL Report & Show in List- Development | 2026-09-23 10:30 | 2026-09-29 02:08 | America/New_York | 7 | * GL report run functionalities implemented * Frontend view for the report data functionalities implemented
Rajib Sarker | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-24 02:00 | 2026-09-25 00:17 | America/New_York | 7 | * Analyze the GL ledger setup and run GL report functionalities * Sit with Tanvir bhai on that * Given estimation on that
Rajib Sarker | FFN-2830 | Delivery App - Internal Issue Fixing - Development | 2026-09-24 11:00 | 2026-09-25 00:16 | America/New_York | 1 | * Packagelane subscription payment issue solved
Rajib Sarker | FFN-2918 | WBS Additional- GL Setup functionalities implementation(CRUD) - Development | 2026-09-25 09:30 | 2026-09-28 01:08 | America/New_York | 7 | * Worked on implementing the GL setup functionalities
Rajib Sarker | FFN-2918 | WBS Additional- GL Setup functionalities implementation(CRUD) - Development | 2026-09-28 11:00 | 2026-09-29 02:05 | America/New_York | 1 | * Resolved PR feedbacks
Rajib Sarker | FFN-2921 | WBS Additional- Run GL Report & Show in List- Development | 2026-09-28 12:00 | 2026-09-29 02:06 | America/New_York | 7 | * GL report run functionalities refactoring * Seed data generates for GL setups
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-01 02:50 | 2026-09-02 05:52 | America/New_York | 3 | 1. Support team members 2. Discussion with Rajib vai on Cash Register 3. Discussion with Tariq vai
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-01 04:50 | 2026-09-02 05:51 | America/New_York | 1 | 1. Review PRs
Tanvir Ahmed | FFN-2641 | Packagelane – Security & Infrastructure Architecture Assessment | 2026-09-01 23:41 | 2026-09-03 03:44 | America/New_York | 4 | 1. Work on exploring the best practice for open telemetry 2. Work on integrating health with azure app service for packagelane
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-02 00:35 | 2026-09-03 03:36 | America/New_York | 3 | 1. Support team members. 2. Discussion with Nayef vai on task updates 3. Attend Client meeting
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-02 02:30 | 2026-09-03 03:30 | America/New_York | 1
Tanvir Ahmed | FFN-2878 | Weekly Task Update Meeting- 02 September 2026 | 2026-09-02 02:34 | 2026-09-03 04:05 | America/New_York | 1.5
Tanvir Ahmed | FFN-2641 | Packagelane – Security & Infrastructure Architecture Assessment | 2026-09-02 02:35 | 2026-09-03 04:05 | America/New_York | 1.5
Tanvir Ahmed | FFN-2683 | Integrate Integration Test in CI/CD Pipeline | 2026-09-02 03:05 | 2026-09-03 04:06 | America/New_York | 1
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-03 01:29 | 2026-09-07 03:30 | America/New_York | 2 | 1. Support team members
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-03 02:28 | 2026-09-07 03:29 | America/New_York | 1 | 1. Review PRs
Tanvir Ahmed | FFN-2641 | Packagelane – Security & Infrastructure Architecture Assessment | 2026-09-03 07:04 | 2026-09-09 10:05 | America/New_York | 3 | Deployed open telemetry to Dev environment
Tanvir Ahmed | FFN-2683 | Integrate Integration Test in CI/CD Pipeline | 2026-09-03 09:43 | 2026-09-09 10:43 | America/New_York | 1
Tanvir Ahmed | FFN-2888 | Delivery App v3.2 UAT CR - Address validation for orders from Trip page | 2026-09-07 06:30 | 2026-09-09 09:32 | America/New_York | 3 | 1. Add address validation feature in trip edit page
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-07 07:27 | 2026-09-09 09:29 | America/New_York | 3 | 1. Support team members 2. Deployed to UAT
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-07 08:27 | 2026-09-09 09:28 | America/New_York | 1
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-08 00:46 | 2026-09-10 04:49 | America/New_York | 3 | 1. Conduct meeting with Atashi and Rajib on GL analysis 2. Do analysis on the meeting, requirements
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-08 03:52 | 2026-09-10 04:52 | America/New_York | 2
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-08 09:46 | 2026-09-09 10:47 | America/New_York | 2 | Review PRs
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-09 00:48 | 2026-09-10 04:53 | America/New_York | 3
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-09 04:03 | 2026-09-10 05:04 | America/New_York | 2
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-09 04:03 | 2026-09-10 05:04 | America/New_York | 1
Tanvir Ahmed | FFN-2892 | Weekly Task Update Meeting- 09 September 2026 | 2026-09-09 04:57 | 2026-09-10 05:57 | America/New_York | 1
Tanvir Ahmed | FFN-2846 | Sprint 43- Project Management- Tanvir | 2026-09-10 00:38 | 2026-09-14 03:39 | America/New_York | 4 | 1. Support team members 2. Deploy to UAT
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-10 00:39 | 2026-09-14 03:40 | America/New_York | 3
Tanvir Ahmed | FFN-2849 | Sprint 43- Code Review- Tanvir | 2026-09-10 02:37 | 2026-09-14 03:38 | America/New_York | 1 | Review PRs
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-11 14:12 | 2026-09-15 17:13 | America/New_York | 3 | 1. Support team members
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-11 14:14 | 2026-09-15 17:14 | America/New_York | 3
Tanvir Ahmed | FFN-2899 | Sprint Review and Planning Meeting | 2026-09-11 15:13 | 2026-09-15 17:14 | America/New_York | 2
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-14 14:52 | 2026-09-15 17:23 | America/New_York | 4.5 | 1. Attend client meeting (2h) 2. Do analysis
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-14 15:21 | 2026-09-15 17:22 | America/New_York | 2
Tanvir Ahmed | FFN-2896 | Internal-Wire Service Shop Sync and Shop Search for Recipient Address | 2026-09-14 16:18 | 2026-09-15 17:18 | America/New_York | 1.5
Tanvir Ahmed | FFN-2913 | WBS Additional - Implement Shipping Slots and Integrate with Shipping Order Type | 2026-09-15 23:00 | 2026-09-17 02:31 | America/New_York | 4
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-15 23:31 | 2026-09-17 02:32 | America/New_York | 3 | Support team members and manage teams
Tanvir Ahmed | FFN-2898 | Sprint 44- Weekly Task Update Meeting | 2026-09-16 01:28 | 2026-09-17 02:59 | America/New_York | 1.5
Tanvir Ahmed | FFN-2913 | WBS Additional - Implement Shipping Slots and Integrate with Shipping Order Type | 2026-09-16 01:40 | 2026-09-17 02:41 | America/New_York | 0.5 | 1. Clean up codes, test and create PR, resolve PR feedback
Tanvir Ahmed | FFN-2914 | WBS Additional- MAS API Portal & Integration - Requirement Analysis | 2026-09-16 01:48 | 2026-09-17 02:49 | America/New_York | 1
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-16 01:54 | 2026-09-17 02:55 | America/New_York | 1
Tanvir Ahmed | FFN-2842 | CR- Checkout Box Order and Release Flow Implementation- Development | 2026-09-16 01:55 | 2026-09-17 02:56 | America/New_York | 1 | Review PRs
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-16 23:41 | 2026-09-17 02:54 | America/New_York | 3 | 1. Support team members
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-17 00:50 | 2026-09-23 03:51 | America/New_York | 2.5
Tanvir Ahmed | FFN-2915 | PackageLane Prototype Creation | 2026-09-17 01:52 | 2026-09-23 03:53 | America/New_York | 2
Tanvir Ahmed | FFN-2842 | CR- Checkout Box Order and Release Flow Implementation- Development | 2026-09-17 02:23 | 2026-09-23 02:54 | America/New_York | 0.5 | 1. Review PR
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-17 23:49 | 2026-09-23 03:51 | America/New_York | 3 | Analysis of GL on different scenarios and see how it behaves against rules setup
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-18 00:54 | 2026-09-23 03:55 | America/New_York | 3 | Support team members Attend Review meeting
Tanvir Ahmed | FFN-2865 | Internal- Wire Service Testing- Nayef | 2026-09-18 02:57 | 2026-09-23 03:58 | America/New_York | 1 | Review PR
Tanvir Ahmed | FFN-2915 | PackageLane Prototype Creation | 2026-09-18 22:55 | 2026-09-23 03:55 | America/New_York | 4
Tanvir Ahmed | FFN-2895 | Packagelane Migration to Linux App Service | 2026-09-21 00:02 | 2026-09-23 04:03 | America/New_York | 4 | 1. Deploy package lane backend to linux app services. 2. Deploy frontend to azure static web app 3. Do R&D on timezones variance in linux and windows
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-21 01:58 | 2026-09-23 03:59 | America/New_York | 2
Tanvir Ahmed | FFN-2915 | PackageLane Prototype Creation | 2026-09-21 01:58 | 2026-09-23 03:59 | America/New_York | 2
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-22 02:21 | 2026-09-23 04:22 | America/New_York | 2 | 1. Support team members
Tanvir Ahmed | FFN-2898 | Sprint 44- Weekly Task Update Meeting | 2026-09-22 02:22 | 2026-09-23 04:23 | America/New_York | 2 | Attend client meeting
Tanvir Ahmed | FFN-2894 | Packagelane Frontdoor Integration | 2026-09-22 02:23 | 2026-09-23 04:24 | America/New_York | 2
Tanvir Ahmed | FFN-2863 | WBS Additional- GL Setup functionalities Configuration- Development | 2026-09-22 03:22 | 2026-09-23 04:23 | America/New_York | 1
Tanvir Ahmed | FFN-2894 | Packagelane Frontdoor Integration | 2026-09-23 00:45 | 2026-09-25 03:45 | America/New_York | 3
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-23 01:42 | 2026-09-25 03:43 | America/New_York | 3
Tanvir Ahmed | FFN-2914 | WBS Additional- MAS API Portal & Integration - Requirement Analysis | 2026-09-23 01:44 | 2026-09-25 03:45 | America/New_York | 2
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-24 01:28 | 2026-09-28 04:29 | America/New_York | 3
Tanvir Ahmed | FFN-2894 | Packagelane Frontdoor Integration | 2026-09-24 02:04 | 2026-09-28 04:35 | America/New_York | 2.5
Tanvir Ahmed | FFN-2620 | UAT 4.0 CR - Allow Creation of Generic User Without Mandatory Employee-Specific Fields (Username/Employee Setup Constraint Issue) | 2026-09-24 03:32 | 2026-09-28 04:33 | America/New_York | 1
Tanvir Ahmed | FFN-2589 | WBS Additional- Internet Order- Development | 2026-09-24 04:02 | 2026-09-28 04:33 | America/New_York | 0.5
Tanvir Ahmed | FFN-2854 | Issue- Batch Payment Issue Fixing- Development | 2026-09-25 03:59 | 2026-09-29 07:59 | America/New_York | 4
Tanvir Ahmed | FFN-2894 | Packagelane Frontdoor Integration | 2026-09-25 05:59 | 2026-09-29 08:00 | America/New_York | 2
Tanvir Ahmed | FFN-2897 | Sprint 44- Project Management | 2026-09-25 05:59 | 2026-09-29 08:00 | America/New_York | 2
Tanvir Ahmed | FFN-2610 | UAT 4.0 CR - Implement fallback logic to use previous Delivery Calendar setup if current date is unconfigured | 2026-09-28 04:00 | 2026-09-29 08:00 | America/New_York | 4
Tarikul Islam | FFN-2897 | Sprint 44- Project Management | 2026-09-29 05:55 | 2026-09-29 07:55 | America/New_York | 2